# Scope Advisor — Revised Spec (Grounded in Course Pedagogy)

**For:** Sai Chakrri Tadikonda

**From:** Scott Burgins, V550 Instructor

## 0. The course's actual pipeline

Every class builds toward this sequence — the Scope Advisor should walk the student through it in this order, not jump straight to "write a charter":

Big 5 Pre-Questions  →  Requirements  →  Expectations  →  Goals & Objectives

→  Deliverables  →  Scope of Work Statement  →  Scope Action Plan  →  Work Breakdown Structure

```

The WBS itself stays with the WBS Decomposer (Stage 1's sub-agent), but everything before it — Big 5 through Scope Action Plan — is Scope Advisor territory. Flag this for scoping the build effort.

## 1. Big 5 Pre-Questions — a short reflective preamble

Before the student writes anything, the lecture has them answer five questions about *their own position*, not the project's content:

| # | Question | What it's really asking |

|---|---|---|

| Q1 | What's our history of project planning? | Is there a track record of success/failure to build on or repair? |

| Q2 | What's your role? | In-house staff, consultant, contractor, subcontractor, support, stakeholder, agency rep? |

| Q3 | How much "juice" do you have? | Are you actually in charge of the steering committee, budget, timeline, final recommendations? |

| Q4 | Who is your patron? | Who's the guardian/supporter who gives you inside knowledge, early warning, and cover? |

| Q5 | What kind of plan is it? | Down-and-dirty quick fix vs. comprehensive long-range/strategic plan? |

**Adaptation problem for a classroom sim:** students don't have a real organizational history or a real patron. I'd adapt these into a short **role-framing exercise** rather than literal questions:

- "What role are you playing — the project's own PM, an outside consultant, or an agency staffer?"

- "What kind of plan is this — a quick, narrowly-scoped plan, or a comprehensive long-range one?"

- "Who's your patron in this exercise?" (Reasonable answer: the instructor, a named fictional supervisor, or an assigned advisor character)

This is optional but valuable — it primes students to think about authority and context before they start drafting, which is the whole point of Q1–Q5.

Make this a required-but-quick, logged as its own milestone event (`role_framing_submitted`), since it costs almost nothing and reinforces a core lesson.

## 2. Requirements vs. Expectations — these are two separate fields, not one

The course draws a hard line here that the original spec collapsed into a single "constraints/assumptions" bucket. Keep them separate:

**Requirements** — non-negotiable, must be met: federal/state law, funder requirements, client-mandated conditions. The advisor should ask directly: *"Are there predetermined requirements — legal, regulatory, funder, or client — that this project must satisfy?"*

**Expectations** — softer, often unstated beliefs about what the project will deliver. The advisor should ask the student to answer these *as if the client were asking*:

- "What's the biggest thing you hope comes out of this project?"

- "What's your biggest fear? What could go wrong?"

- "What are other stakeholders expecting of this project?"

Then run a **MoSCoW pass** on the expectations: Must-have / Should-have / Could-have / Won't-have. This is a natural place for a short structured sub-step — not necessarily a new sub-agent, but a distinct prompt in the Scope Advisor's flow, logged as its own event (`moscow_submitted`).

## 3. Goals vs. Objectives — enforce the distinction, enforce SMART

The course is explicit that these aren't interchangeable:

- **Goals**: not measurable, long-term, directional ("provide excellent customer service")

- **Objectives**: measurable, phrased so they can be turned into a yes/no question ("reduce customer wait time to one minute")

**Hard rule for the Auto-Grader / Assumption Auditor:** every objective the student writes must pass the SMART test — Specific, Measurable, Achievable, Relevant, Time-based. If an objective can't be rephrased as "Did I accomplish X in Y time?" it gets kicked back. This is a concrete, checkable rule an LLM critique agent can actually apply consistently — worth hard-coding into the Assumption Auditor's prompt rather than leaving to judgment.

## 4. Deliverables — sequenced, not dumped at the end

Deliverables must be:

- Tangible or intangible outputs (not activities)

- **Phased** — delivered one at a time with sign-off before the next, not all handed over at project end

- Each tied to a point where the "client" (in this course, the Review Board) approves before moving on

Example structure from the lecture (community development project): Vision & Goals → Demographic Profile → Evaluation of Existing Conditions → Stakeholder & Public Input → Draft Recommendations → Adoption of Final Plan. Each is its own sign-off point.

For the Scope Advisor, this means the deliverables list should come with an implied or explicit **order and dependency**, not just a flat list — which sets up the WBS Decomposer nicely, since PMBOK-style WBS is often organized by deliverable.

## 5. Scope of Work Statement — the actual PMBOK components

A complete Project Charter, per the Class 10 rubric slide, has these parts:

| Component | What it contains |

|---|---|

| **Project Statement** | Trigger (what problem triggered this?) + Action (what will be done?) + Frequency & Timing (one-time vs. ongoing, linked decisions?) + Scope (how broad/complex?) + Assumptions, Constraints & Uncertainty |

| **Objectives & Success Criteria** | SMART objectives; success criteria are tangible, quantifiable indicators tied 1:1 to each objective |

| **Scope of Work** | High-level: what's expected but not yet scheduled/detailed |

| **Deliverables** | Logically ordered/phased (see above) |

| **Scope Action Plan** | See Section 6 below — new artifact, not previously in the spec |

| **Constraints & Uncertainties** | Explicit limitations (budget, time, legal) and named uncertainties/risks not yet resolved |

| **Project Exclusions** | Explicitly what is *not* included — this is the course's primary defense against scope creep and deserves its own labeled section, not a subheading under constraints |

## 6. Scope Action Plan —sits between Scope Statement and WBS

It's the bridge between "what we'll deliver" and "how we'll actually do it," and the course treats it as a distinct, gradable artifact.

**Format:** one action-verb sentence per activity, tied directly to a deliverable. Verbs like *Undertake, Produce, Commission, Identify*. Example from the lecture:

1. *Undertake research to determine the number of homes in the area.*

2. *Produce a design for the recycling bins.*

3. *Commission a supplier to manufacture the bins per the design in (2).*

4. *Identify and implement a distribution method.*

**Hard rule from the course, worth encoding as a critique prompt:** a PM should *not* draft this alone ("Lone Wolf") — in a real team, it requires buy-in from every teammate on their role. Since V550 students work solo, the advisor can't enforce real buy-in, but it can simulate the check by asking the student to justify *why* each task is assigned the way it is, and flag any action-plan item that has no owner.

**New sub-agent question:** should Scope Action Plan generation live inside the WBS Decomposer (since it's adjacent), or does it need its own light-weight sub-agent? I'd lean toward folding it into WBS Decomposer's scope rather than adding a 10th specialist — it's a short, formulaic artifact, not a complex reasoning task. Your call on build effort.

## 7. WBS — reinforcing existing spec, three additions

Three things from the lectures worth baking into its prompts:

1. **The specificity test**: "Find demographics on poverty" is too vague; "Use U.S. Census top indicators of poverty; compile from American Community Survey" is the target level. The WBS Decomposer's critique of MECE violations should include a vagueness check, not just overlap/gap detection.

2. **The chunking rule**: tasks should be sized to roughly 60-minute or 1-week units. Might be a useful automatic flag ("this WBS line is too large — break it down further") rather than just leaving depth-consistency to the model's judgment.

3. **Common WBS failure modes** the auditor should watch for, straight from the course: not taking estimates seriously, too much/too little detail, one voice dominating, overcomplicating structure, adding requirements instead of tasks, skipping buy-in, ignoring soft factors like team dynamics.

## 8. Ready-made Auto-Grader rubric

The course already has a Project Charter rubric (Class 10, slide 40). Recommend using it close to verbatim for the Scope Advisor's gate:

| Dimension | What's being scored |

|---|---|

| Project Statement | Trigger / Action / Frequency & Timing / Scope / Assumptions, Constraints & Uncertainty — all present and coherent |

| Objectives & Success Criteria | SMART objectives; criteria are tangible and quantifiable |

| Scope of Work | Clear high-level in/out boundary |

| Deliverables | Logically organized and phased |

| Scope Action Plan | Every deliverable has action-verb steps; steps are assignable |

| Constraints & Uncertainties | Anticipated issues and risks named |

| Exclusions | Explicit, not just implied |

| "Do you deliver?" | Holistic: would a PM confidently put their name on this? |

I'd score each 1–5 with rationale, same pattern as your existing Auto-Grader design — this just replaces the placeholder four dimensions with the course's real eight.

## 9. Revised answers to your original open questions

A few of my earlier answers change in light of this:

- **Charter fields (Section 4 of my last doc)** — superseded by Section 5 above. Use the Project Statement / Objectives / Scope of Work / Deliverables / Scope Action Plan / Constraints & Uncertainties / Exclusions structure, not the generic purpose/objectives/success-criteria list.

- **"Should Stage 1 collect team size, budget, etc.?"** — still no, same reasoning as before (defer to Resource & Cost Advisor). Nothing in the lecture material changes this.

- **"What's the minimum acceptable detail?"** — now answerable concretely per field via the rubric table above, rather than my earlier generic guidance.

- **Good/weak examples** — the lecture already has strong real ones (the Owen County marketing partnership Project Statement, the recycling bin Scope Action Plan, the bridge design Scope of Work). I'd pull directly from the deck rather than inventing new placeholders — more authentic and consistency-checked against what students already saw in lecture. Want me to extract a clean anonymized example set from these slides for the knowledge file?

---

## Open decisions for me before Sai builds this

1. Is Big 5 role-framing required-but-quick, or optional?

2. Does Scope Action Plan get its own sub-agent, or fold into WBS Decomposer?

3. Should the knowledge-file examples be pulled directly from these lecture decks (anonymized) rather than freshly generated?