Scenario 1 Scope of Work

After the Merger: One Building, Nine Desks

Before You Read the Scenario

You are going to work through this scenario with an AI agent that will not simply accept what you give it. It checks your work at six points, and at each one it can send you back.

Two kinds of checks are running. Some are factual — the agent knows the scenario and will stop you if your work contradicts it. Those are not negotiable and the agent will not fix them for you; it will tell you what you got wrong and wait.

Others are judgment — the agent will tell you when your reasoning is thin, but you decide whether to revise. Many different answers can be right. The agent is also wrong sometimes. Part of your grade is noticing when, saying so, and documenting why you overrode it. An AI that pushes back is a tool, not an authority.

The Situation

In March 2022, three Bloomington arts organizations — Bloomington Playwrights Project, Cardinal Stage, and Pigasus Institute — announced a three-way merger. That announcement is real. Everything else below is invented for this course. Do not research what actually happened. It is not the situation you are in, and the agent will not recognize it.

Where things stand

The merger closed eighteen months ago, creating Meridian Arts Collective. Three legacy programs continue under the new name:

New Play Development — commissions and workshops new scripts, runs a spring festival of staged readings.

Mainstage — a five-show subscription season, September through May.

Learning & Media — youth theater classes, adult workshops, a small documentary film program.

Meridian has 11 full-time staff and about 30 contract artists per season. The three legacy artistic leads all stayed on and now report to Executive Director Dana Okoye, hired from outside all three organizations eight months ago. Everyone is polite in meetings. Nothing about space has been settled.

How Meridian plans

The merger itself was planned by an outside consultant: $90,000, fourteen months, a 214-page integration plan. The governance and branding sections were carried out. The facilities and programming sections were not. Staff call it "the binder."

Since the merger, Meridian has run two internal projects. A website consolidation finished four months late. A donor database merge was abandoned after five months, with no written record of why.

Legacy Mainstage staff describe the merger as something done to them. Legacy Learning & Media staff describe it as something done around them. Nobody currently on staff has run a formal planning process in-house.

The building

Meridian leases the John Waldron Arts Center from the City of Bloomington — roughly 38,000 square feet.

Space	Detail

Ruth Auditorium	232 seats, fixed seating, full fly system

Firebay black box	87 seats, flexible configuration

Main Gallery		2,100 sq ft, street-facing

Corridor Gallery	900 sq ft

Studios A–F		six rooms, 400–800 sq ft each

Scene shop		basement, 1,800 sq ft, shared

Admin suite		second floor, nine desks

One loading dock. One freight elevator.

A 2019 space utilization study, commissioned by the building's previous operator, sits unread in a filing cabinet in the admin suite. It contains floor plans, room dimensions, and a full year of booking data.

Money and time

The facilities planning budget is $35,000 — enough for a facilitator (local rate $1,200/day), printing, room-scheduling software, and stipends for outside participants. It does not cover staff time. There is no capital money: you cannot renovate, move a wall, or buy equipment.

January 12 — kickoff

March 19 — Board Facilities Committee meets, expects a progress update

May 14 — full board votes on the allocation plan

June 1 — 2027–28 season announced publicly

Programming cannot build the 2027–28 season until allocation is settled.

Your role

You are Marcus Feld, Director of Operations. Dana's email says you will "lead the process." Nothing further is in writing, and no announcement has gone to staff.

You control the meeting schedule, who gets consulted, the format of the final recommendation, and the $35,000.

You do not control the final allocation decision (the board votes), whether the three legacy artistic leads participate (they report to Dana), the 2027–28 season calendar (programming staff), or anything in the lease.

Nobody has been assigned responsibility for the fallout when a legacy lead is unhappy with the outcome, or for speaking to the City. Dana has said she will not referee between the three legacy leads.

Your team — three people, 0.75 FTE combined

- Marcus Feld (you), 0.4 FTE. Also managing front of house, facility rentals, and the building maintenance contract.

- Priya Raghavan, Associate Director of Learning & Media, 0.2 FTE. Also teaching two class sections.

- Tomas Beltrán, Production Manager, 0.15 FTE. Also running the current season. He has worked in the Waldron for eleven years — longer than anyone else at Meridian.

- Everyone else

The three legacy artistic leads. New Play Development wants the Firebay available year-round for workshops. Mainstage wants the Ruth plus the Firebay for rehearsal during tech weeks. Learning & Media wants four studios on a fixed weekly schedule, and notes that its enrollment is the only line that grew last year.

Ruth Adeyemi, board member, chairs the Facilities Committee. Retired City Parks & Recreation director. Negotiated the original Waldron lease in 2016. Attends few meetings; answers email within a day.

Gwen Tsai, City Arts Commission liaison. Administers the lease. Has no authority inside Meridian, but decides how strictly the community-access requirement gets audited.

Outside tenants. A dance school holds Studios C and D every Tuesday and Thursday, 4–8 p.m., under an agreement running through August 2028. Six community groups rent studios monthly with no written agreements.

Visual artists. The Main Gallery exhibition calendar is contracted 14 months out.

Staff. Nine desks. Eleven full-time employees.

Constraints

- The City lease requires 900 hours per year of community access at below-market rates. Meridian currently documents 515.

- Dance school agreement runs through August 2028.

- Gallery calendar contracted 14 months out.

- $35,000, no capital funds, staff time not covered.

- Board vote May 14; season announcement June 1.

- 0.75 FTE of team capacity.

- Fire code occupancy limits and ADA access requirements apply throughout.

Out of scope

Real problems, but not for this project.

- Renovation, construction, or any capital campaign

- Staff restructuring or layoffs

- Merging the three legacy ticketing systems

- Renegotiating the City lease

- Choosing the 2027–28 season's shows

What You Are Doing

Working in your pod, you will build a scope of work for the Waldron allocation project, moving through six checkpoints with the agent. Each one has to open before the next becomes available.

- Big 5 Pre-Planning — the five questions you ask about your own situation before planning starts

- Requirements — what must be satisfied

- Expectations — what people want, sorted by MoSCoW

- Goals & Objectives — one goal, SMART objectives

- Scope of Work — project statement, scope statement, exclusions, deliverables, and the scope action plan

- Work Breakdown Structure — the work itself, decomposed and costed

Together these produce the components of your project charter.

Deliverables

[instructor to specify — charter document, agent transcript, and override log]

Due: [instructor to specify]

Read the Slides First.

The agent checks your work against the frameworks taught in this course, not against generic project management. It is looking for specific things from specific class sessions:

- The Big 5 are five questions about your own position. If you show up thinking they are a list of stakeholders, Checkpoint 1 will not open.

- Requirements and expectations are different categories, and the class defines each precisely. Guessing at the difference will cost you attempts.

- Goals and objectives are distinguished by measurability, and the class gives you a specific test for whether an objective qualifies.

- The project statement has a fixed set of components. Not four. Not a paragraph.

- Scope action plan statements begin a particular way. The class is explicit about this and the agent checks it mechanically.

- The WBS has a stated standard for how specific a work package must be, and a stated range for how big a chunk should be.

Students who work from memory or from what ChatGPT thinks project management looks like will get stuck at checkpoints that students who reviewed the slides walk through. Open the decks before your first session, not after your third failed attempt.

Tip Sheet

- Read the whole scenario before you start. Details in one section constrain answers in another. The building, the calendar, and the budget are one problem.

- Watch the numbers. Some of them are in tension with each other. That tension is the project.

- Notice what nobody has decided. Several important things in this scenario have never been assigned, put in writing, or announced. Those gaps are not oversights in the assignment.

- Do not solve it in checkpoint one. The most common failure is deciding which program gets which room early, then writing requirements that justify the answer you already picked. The agent is built to catch this.

- When the agent stops you on a fact, it will not fix it. It will name the contradiction and wait. Go back to the scenario.

- When the agent gives you judgment feedback, you may proceed anyway. Doing so is legitimate. Record why — that reasoning is graded.

- Keep your prior answers open. From checkpoint two onward, the agent compares your new work against what you told it earlier. Contradicting yourself is a common and avoidable problem.

- Do not research the real merger. The scenario diverges from it deliberately, and outside facts will make your work inconsistent.

- Track your time. You have 0.75 FTE and about seventeen weeks. If your plan would take more than that, it is not a plan.